## Sheet1
COMMENTS | Where resolved
John Jones Nov 21
The Construction Environmental Management Plan that has been submitted (Section 3 of the Site Management Plan) does not provide the necessary site specific detailed measures that will be implemented. The submitted CEMP is a generic document with many matters to be finalised. Furthermore, the CEMP appears to be a draft document that still contains annotated queries. Additionally, the CEMP refers to an Environmental Action Plan (ENV0000009C-JAC-ZZ-00-RP-EN0006) for the works. It does not appear that any document with this reference number has been provided. It should be ensured that all appendices to the final CEMP are provided before the planning condition is discharged. | Action plan to be included in documents. We have also provide a separate list of all docs/drwgs referenced in the CEMP the majority of these were issued previously. See Appendix B
John Jones 24th January 2022
The revised CEMP still lacks details relevant to ecology, that would normally be included within a Construction Environmental Management Plan, and which are needed in order to meet the ecology related requirements of Planning Condition 10 (above). In particular, I recommend that before Condition 10 is discharged, the applicant should be required to add the following information to a project specific CEMP to be submitted for approval: | New CEMP seperated out from less project specific details.
Plans showing the layout of the development site during the construction Phase, clearly showing the location of: | Environmental constraints plan now provided ENV0000009C-JAC-ZZ-ZZ-DR-EN-0004
Site boundaries/Access routes/Compounds and storage areas/Working areas | In Constraints plan
Ecological constraints and risk areas | In Constraints plan also in CEMP section 2.1
Biodiversity protection zones and retained habitats/trees | In Constraints plan plus Tree Root Protection Area plans
The alignment of fencing to protect retained trees, habitats, and biodiversity protection zones etc. | Tree Protection Plans
The location of any barriers for the protection of species that may enter the construction area. | Ecological advise taken that this is not necessay as long as other mitigations are followed re open trenches etc.
The location of any lighting, demonstrating that light spill onto biodiversity protection zones and sensitive ecological receptors (such as water courses and tree canopies) will be avoided. | Covered in text section 2.10
Location of sensitive areas with restricted access. | in constraints plan
Compliance with BS42020 should be added to Section 3.1 (Environmental Standards). | Added now section 1.8
Details of identified risks of each construction operation to each sensitive receptor. | included in a table of operations section 3
Further details to address Condition 10b - Control of noise from construction operations in relation to ecological receptors, including identification of ecological receptors likely to be affected and details of control measures to be implemented. | Covered in table section 3
Further details of proposed measures for the protection of trees and vegetation to be retained as required by Condition 10h. This should include the location of barriers/fencing (including plans as above), barrier/fencing types, installation methods, monitoring, maintenance and removal methods. | Added to section 2.3.6
Dates and survey areas for pre-works surveys for protected and priority species required by planning condition 10i. | Added to section 2.3.1
A rationale for the size of the proposed buffer zone around nesting birds should be provided with reference to best practice guidance. | Best Practice advice given by Jacobs ornithologist
Measures to prevent protected/priority species from entering high-risk working areas, whilst maintaining potential routes through the site and avoiding any obstruction of access to resting places/breeding sites/feeding resources etc. | Covered in section 2.3
Details of measures to be implemented to avoid any breach of wildlife protection legislation, with reference to specific offences stated in legislation and species that could potentially be affected. | Covered in section 2.3
Further details of the functions to be performed by the proposed Ecological Clerk of Works, including frequency and timing of surveys, inspections and supervision visits and details of the operations that they will undertake or supervise (for example, periodic checks for protected /priority species, watching briefs during vegetation clearance/earth works, inspection of excavations etc). | See section 1.10 and Appendix A
A project specific programme of operations relevant to ecology. | See section 3
Contingency plans to be implemented if additional ecological constraints are identified during works, including (but not limited to) the unexpected occurrence of protected species and/or the need for additional licences/consents etc. | See section 1.13
Animal welfare precautions and procedures to be adopted if injured animals are encountered. | See section 2.14
Post construction monitoring and measures to ensure successful re-establishment of disturbed areas. | See section 1.14, 2.12 see also LHEMP and Landscape Specification
Periodic review of the CEMP and how this will be informed by monitoring. | See section 1.14, 2.12 and LHEMP
Record keeping and reporting systems. | See section 1.12 and Appendix A
Further detail of training/toolbox talks for site operatives. | See section 1.11 and Appendix A
All other relevant details as laid out in British Standard BS42020 Biodiversity – Code of Practice for Planning and Development, Section 10 Implementation of development: biodiversity on construction sites, in particular, Section 10.2, Construction Environmental Management Plan (CEMP). | Throughout
Steve Bretton 21/01/2022
Regarding landscape resources this condition states, amongst other things, that "No development shall commence until a construction environmental management plan (CEMP) has been submitted to and approved in writing by the County Planning Authority. The CEMP shall include details of the following:
h) Protection of trees and vegetation to be retained."
The applicant's specific information relating to this is contained within 3. Operational Control, Trees of the Site Management Plan Ref H01-01. Unfortunately, as evidenced by the following, insufficient information has been provided and some of the statements need further clarification: | Section 2.3.6 of the CEMP provides more details.
a) "No felling/pruning/crown raising and the like of trees shall commence until approved in writing by the Local Planning Authority and the Client." | This has been amended see section 2.3.6
Presumably, this relates to additional tree removal/works rather than those already approved? | This does relate to additional works this has been updated in section 2.3.6
b) "Protection shall be afforded to retained trees for the duration of construction work and changes of ground level within the root protection areas."
The latter part of this sentence does not make sense. | Agreeed this has been amended in section 2.3.6
c) "Tree protection fencing to be in accordance with BS5837 and is to be erected before any work commences in the surrounding area."
Where is the fencing to be erected? | Tree root protection plans are now provided which show the locations for fencing and furhter details have been added to section 2.3.6
d) "Excavation within Root Protection Areas shall be by manual means"
Excavation within a root protection area (RPA) should be avoided as considerable damage to and/or loss of roots can occur. Will the excavation within RPA's really be undertaken by "manual means," i.e., by hand? I ask because the replacement flood wall for example would likely require a considerable amount of excavation to remove old foundations and prepare for the new foundations. It may not be even possible to remove the old foundations – especially if they are concrete – by hand. Where excavation is proposed within tree RPA's (as can be seen for example on dwg. ENV0000009C-JAC-ZZ-ZZ-DR-L0016 Rev C03), what evidence has been provided which demonstrates that excavation can be done within them without adversely affecting the tree's long-term health and viability? | This statement was incorrect and has now been amended in section 2.3.6
e) "… Stevin’s Arboriculturist (TBC) has confirmed that no tree roots are present and/or they are protected."
It seems extremely unlikely that there would be no tree roots within a RPA. How would/could the roots be protected if excavation is being undertaken directly where they are? | This is correct we have now amended that statement tp provide a clearer protocol see section 2.4.6
f) "Exposed tree roots will be protected as per the recommendation from the Arboriculturist"
How would the roots be protected? | Arboricultural advice will be provided.
g) "The EA Project Manager shall be notified if there is a clash between the tree roots exposed and construction work."
Details of what happens next should be provided as with tree roots exposed a fast response is critical. | This has been amended in section 2.4.6
h) "Any damage to tree roots (or other contravention of the above requirements) must be reported to the EA Supervisor"
With appropriate precautionary measures informed by an arboricultural assessment, no root damage should occur as a consequence of the proposed works. | This has been amended in section 2.4.6
In addition to the above, no information has been provided on tree protection measures for other works, e.g., grass seeding, within RPA's. Measures are proposed to protect tree RPA's during construction/engineering works, but it is not clear what methods will be used when these have been completed and the RPA fencing removed. | Section 2.4.6 now includes reference to maintianing tree root protection for the duration of the works including follow up landscapeing establishment.
Until the above have been addressed in detail, I recommend that planning condition 10 is not discharged.